## To-Do List
2017 | [7 empty] | 2017
TO-DO LIST GENERAL PROJECT
| Task | Priority | Status | Start Date | Due Date | % Complete | Done/Overdue? | Notes
| Improve the global design | High | In Progress | 2017-09-12 | 2017-12-12 | 10% | -1
| Meeting with Nathalie Debard about animations | Normal | Complete | 2017-09-25 |  | 100% | 1 | Meeting planed in Lausanne
| write case studies | High | In Progress | 2017-09-26 | 2018-03-01 | 0% | -1 | See with Olivier
| make video and audio tutorials | Low | Not Started | 2017-12-01 | 2018-03-01 | 0% | -1
2017 | [7 empty] | 2017
TO-DO LIST SPECIFIC TASKS
| Task | Priority | Status | Start Date | Due Date | % Complete | Done/Overdue? | Notes
| update cases tudies app with the new design | High | Not Started |  |  |  | -1
| update treatments app with the new design | High | Not Started |  |  |  | -1
| add the legend on the background | Normal | Not Started |  |  |  | -1 | see with Tara
| color code inside sliders | Normal | Not Started |  |  |  | -1 | ask with shiny developpers

## todo case studies app
TO-DO LIST SPECIFIC TASKS
Task | Priority | Status | Start Date | Due Date | % Complete | Done/Overdue? | Notes
start the app by a case study from the literature | Normal | Not Started |  |  |  | -1
end the app with a quiz | Normal | In Progress |  |  | 50% | -1
write base case with dashed line | Normal | Not Started |  |  |  | -1
-1

## todo treatments app
TO-DO LIST SPECIFIC TASKS
Task | Priority | Status | Start Date | Due Date | % Complete | Done/Overdue? | Notes
put notifications in red when not compatible with life
add kidney failure
-1
-1